## Read Me
RIDGELINE CONSTRUCTION — Project Template
TABS
Settings · Specifications (descriptions) · Estimate (pricing) · Schedule.
PRICING (cost ▸ markup ▸ ext ▸ tax ▸ total)
Enter My Cost & Markup % in the yellow INTERNAL columns (right). Ext Cost = cost + markup = the
customer's pre-tax price. Those internal columns are outside the print area — never printed.
DESCRIPTIONS & PRINTING
Click a blue cost code to jump to its description on Specifications. Run PrintPacket (Alt+F8) for the
clean packet: Specifications ▸ Estimate ▸ (optional) Schedule.
MACROS (import Ridgeline_Macros.bas: Alt+F11 ▸ File ▸ Import)
AddCostLine · DeleteCostLine · AdoptSuggested · BuildScheduleFromToggles · PrintPacket · ExportScheduleICS · PublishProject.
Prefer no macros? Ask me to publish or export a calendar and I'll do it here.
Deck job? AddCostLine under 0310 → 'Materials - Deck package', Suggested $ ='Material Estimate'!$H$65.
SETUP — do this ONCE, then reuse as a template
You only install the macros one time. After that, save this file as a template and every new job
copied from it already has them — no re-importing per project.
1. File ▸ Save As ▸ type = 'Excel Macro-Enabled Template (*.xltm)' (or *.xlsm for a master copy).
2. Alt+F11 ▸ File ▸ Import File ▸ Ridgeline_Macros.bas (adds AddCostLine, AdoptSuggested, PrintPacket, etc.)
3. Alt+F11 ▸ double-click the 'Schedule' sheet ▸ paste the code from Schedule_Status_Automation.txt.
4. Save. Done — the macros and status automation now live inside the file.
NEW PROJECT each time: File ▸ New ▸ (pick this template) — or just copy the .xlsm and rename it.
Updating the macros later? Alt+F11 ▸ right-click the old 'RidgelineTools' module ▸ Remove (No to export) ▸ re-Import.
Import = the .bas (buttons). Paste into the Schedule sheet = the .txt (auto status behavior).

## Settings
RIDGELINE CONSTRUCTION
Estimate + Schedule - master project template
Project Information
Project / Client | Truesdell SFD
Project Address
Estimate # | EST-1001
Takeoff Quantities (drive the Suggested $ column)
Living space SF | 1800 | Heated area; drives $/sf, flooring, framing, etc.
Garage SF | 400
Covered porch SF | 120
Deck SF | 0
Covered deck SF | 0
Exterior concrete SF | 600
Driveway length (lf) | 40
Foundation wall (lin ft) | 190
Avg foundation wall ht (ft) | 4
Avg ceiling ht (ft) | 9
Exterior wall SF | 1710 | foundation lf x avg ceiling ht
Tile area SF | 400
Remaining floor SF | 1400 | living minus tile (to LVT/laminate)
Kitchen run (lin ft) | 20 | Counter + upper & lower cab length
Windows (qty) | 18
Exterior doors (qty) | 3
Sliding glass doors (qty) | 1
Garage doors (qty) | 1
Total under roof | 2320 | Living + garage + covered porch
Gable area SF | 0 | Added to siding labor/paint & material totals
Assumptions
Sales Tax % | 7.9% | Shown to customer; applied to taxable lines
Default Markup % | 20% | INTERNAL margin - drives every non-passthrough line
Project Start Date | 2026-07-01 | Schedule + milestones flow from this
Company / Branding
Company | Ridgeline Construction
Mailing | PO Box 516, Longview, WA 98632
Phone | 360-200-1716
Milestone Anchor Dates (auto from start; edit as needed)
Financing | 2026-07-01
Permitting | 2026-08-01
Foundation | 2026-09-01

## Specifications
SPECIFICATIONS
PO Box 516, Longview, WA 98632 • 360-200-1716
Project: Truesdell SFD Estimate EST-1001
Code | Item & Specification
0100 | General Conditions
0110 | Permits (Allowance)
Builder will prepare and submit applications for the standard building, mechanical, plumbing, and electrical permits required by the jurisdiction. The permit allowance covers typical permit fees and is billed at actual cost. Not included: planning/design review, SEPA or environmental review, impact, traffic, school, or park fees, and any plan-revision fees — these are billed in addition if required. Owner is responsible for HOA submittals and approvals.
0120 | Electrical Utility Connections (Allowance)
Electric: connection to public power including transformer and meter base. Service is assumed available at the road adjacent to the property line; trenching, conduit, or boring beyond that point is not included. Gas (if applicable): coordination of the gas service connection to the meter — confirm provider and tap location. Cable / phone / internet: owner coordinates underground installation with Comcast & CenturyLink and arranges activation after taking possession.
0130 | Excavation (Allowance)
Strip and stockpile existing topsoil on site where practical. Excavate for the foundation to plan bottom per the architectural drawings; spoils are stockpiled for backfill. Unknowns: unsuitable or unstable soils (rock, soft clay, sinkholes, high water table) cannot be priced before excavation and are billed as a change if encountered. Builder backfills with existing soils, rough-grades excess on site, and spreads stockpiled topsoil over disturbed areas. Owner is responsible for seeding, irrigation, fertilizing, and final yard. Not included: import of additional topsoil, off-site haul of excess spoils (except demolition debris), hidden/undisclosed wells, tanks, or pits. Erosion control (silt fence) installed and maintained per permit.
0140 | Septic system design & install (Allowance)
Design, permitting, and installation of an on-site septic system, assumed to be a pressure-distribution system without pretreatment. Includes tank, pump, drainfield, control panel, and float alarm. Final engineered design and health-department approval are required to confirm system type, size, and cost; pretreatment (if required by the site/soils) is an added cost.
0150 | Well setup (Allowance)
Well pump, pressure tank, controller/pressure switch, and wiring from the panel to the well. Not included unless noted: well drilling, well house/pump house, and water treatment — coordinate with the well driller. *(Currently $0 — confirm whether the lot is on a well or public water.)*
0190 | Job site services
General conditions for the duration of the project: temporary toilet maintained on site, dumpsters/debris removal as needed, and ongoing site cleanup. Professional rough and final cleaning, with a detailed final clean before the owner orientation/walkthrough. Temporary power and water as needed during construction.
0200 | Site Work
0210 | Footing And Foundation
Form and pour concrete footings and foundation walls per the structural drawings and IRC, including rebar, anchor bolts, and hold-downs. Includes footing/perimeter drain, damp-proofing of below-grade walls, and under-slab vapor barrier where slabs occur. Pricing is based on the current drawings; additional steps, taller walls, or engineered changes are billed as a change.
0300 | Rough Structure
0310 | Framing Materials (Allowance)
All lumber and framing materials sized and spaced per the approved construction drawings; lumber to be #2 or better, kiln-dried. Floor sheathing 1‑1/8″ Edge Gold T&G OSB; wall and roof sheathing 7/16″ OSB with H-clips where applicable. Floor framing engineered I-joist or per plan; roof trusses/rafters per plan with vaults as drawn. Includes structural connectors, hangers, hold-downs, and fasteners.
0320 | Framing Labor
Construct the rough structure per the plans and engineering: floor system, walls, roof structure, and wall/roof sheathing. Includes setting exterior doors and windows, installing structural hardware, and providing solid backing for cabinets, railings, and bath fixtures. Includes shear-nail and framing inspections.
0400 | Windows & Doors, Exterior
0410 | Front Door (Allowance)
Entry door per the drawings — allowance covers the door slab/unit, jamb, weatherstripping, and exterior hardware/lockset. Sample: 3/0 × 8/0 knotty alder. Decorative glass or custom sizes may affect the allowance.
0420 | Other exterior doors
Remaining exterior doors per plan (e.g., man-doors, patio/utility), including jambs, weatherstripping, and hardware. Sliding/French patio doors are itemized under Windows.
0430 | Garage Doors
Garage door(s) sized and quantity per plan. Spec: Clopay Bridgeport, steel, 2-layer insulated (R-6.3), white — e.g., 18′×8′. Includes track, springs, weather seal, and opener(s) with two remotes and exterior keypad (confirm opener count = door count).
0440 | Windows (Allowance)
Windows per plan — Milgard vinyl, white standard (other colors available at added cost). Includes Low-E / argon insulated glass, screens, and tempered glass where required by code (near doors, in wet areas, large/low units). Includes sliding glass door(s) per plan. Egress windows sized per code at sleeping rooms.
0500 | Exterior Finishes
0510 | Siding Materials
Fiber-cement lap siding (Hardie), 7″ reveal; finger-joint primed cypress trim at corners and windows; primed cypress fascia/barge; cedar tongue-and-groove porch ceilings; LP soffits. Includes weather-resistive barrier (house wrap) and flashing/trim accessories.
0520 | Siding Labor
Install the weather-resistive barrier, window/door flashing, exterior trim, siding, soffits, and post wraps per the drawings, including all caulking and sealing.
0530 | Roofing Specifications (Allowance)
30-year architectural composition shingles over synthetic underlayment, with ice-and-water shield at eaves/valleys, drip edge, step/counter flashing, and ridge ventilation. Pipe boots and roof penetrations flashed and sealed. Color per owner selection.
0540 | Gutters
5″ K-style seamless aluminum gutters with downspouts, white standard (colors available; paintable to match trim). Includes hangers and splash blocks; downspouts discharged to daylight or drains per grade.
0550 | Exterior Masonry
Manufactured (cultured) stone veneer at locations shown — includes lath, scratch coat, stone, and sealing. *(Currently $0 — confirm scope/locations.)*
0560 | Exterior Painting
Two coats exterior latex on all trim and siding — one color per siding type and one trim color. Exposed natural wood receives one coat semi-transparent sealer. Includes surface prep and caulking touch-up.
0570 | Concrete Flatwork (Allowance)
Exterior flatwork per plan — driveway apron, front patio, and walkways. Minimum 3.5″ thick, 3,000 psi concrete over a compacted gravel base, with fiber/wire reinforcement, control joints, and a broom finish. Confirm driveway scope (full vs. apron only).
0600 | HVAC
0610 | HVAC
Complete heating and cooling system per plan, sized per a Manual J load calc — equipment, supply/return ductwork, registers, and programmable thermostat(s). Includes whole-house ventilation, bath exhaust fans, range-hood and dryer venting to exterior. Confirm system type (heat pump / gas furnace + AC) and number of zones.
0620 | Fireplace (Allowance)
Gas fireplace insert/unit per plan and owner selection, including direct-vent termination and install. Gas line to the unit is provided under Plumbing. Surround, mantel, and hearth finish are under Interior Masonry (1160).
0700 | Plumbing
0710 | Plumbing (Allowance)
Complete plumbing system per code: PVC DWV drainage, PEX water distribution, two frost-proof exterior hose bibs, and fixtures/trim per plan. Includes water heater, pressure-reducing valve, and gas piping to furnace, water heater, fireplace, range, and dryer as applicable. Confirm water heater type (tank vs. tankless) and fixture allowance.
0800 | Electrical
0810 | Electrical (Allowance)
Complete electrical per plan: 200A panel and meter, branch wiring, and all 240V circuits for listed appliances. Standard lighting layout — recessed cans in kitchen, dining, master, and covered porches; surface fixtures elsewhere; white tamper-resistant devices and rocker switches; white LED trims on cans. Includes smoke/CO detectors per code, exterior GFCI outlets, and bath/kitchen GFCI/AFCI protection. Surface-mount fixtures are owner-provided (see 0720); installation is included.
0820 | Electrical Fixtures (Allowance)
Decorative/surface-mount fixtures — ceiling fans, dome lights, chandeliers, pendants, sconces, vanity lights, outdoor lanterns, and security lights — are owner-provided. Builder installs owner-supplied fixtures (labor included under Electrical). Provide fixtures on site before trim-out.
0900 | Insulation
0910 | Insulation
R-23 blown-in blanket (BIBS) in exterior walls, R-60 blown insulation at flat ceilings/attic, and R-38 in the crawl space where accessible. Includes air-sealing of penetrations, attic baffles for ventilation, and a vapor retarder per code/climate zone.
1000 | Interior Wall & Ceiling Finishes
1010 | Drywall
1/2″ gypsum board throughout — orange-peel texture on walls, machine brocade on ceilings; square, bullnose, or baby-bullnose corners per selection; 3-way drywall wrap at windows with sill trim. Moisture-resistant board at wet areas and 5/8″ Type-X at the garage/house separation per code.
1020 | Interior Paint
Prime, then spray and back-roll two finish coats — up to two wall colors, one ceiling color, and one trim color. Includes patch/prep and final touch-up after trim and flooring.
1030 | Interior Paint Color(s)
Owner color selections recorded here (no separate cost). Final selections due before paint to hold schedule.
1040 | Bathroom accessories and mirrors (Allowance)
Allowance for bath accessories — toilet-paper holders, towel rings/bars, robe hooks, and vanity mirrors — one set per bathroom. Builder installs owner selections.
1050 | Masonry - Fireplace facade (Allowance)
Cultured-stone facade on the fireplace wall, including lath, scratch coat, stone, and a wood mantel. *(Currently $0 — confirm scope/height.)*
1100 | Flooring
1110 | Flooring Labor (Allowance)
Install owner-selected flooring throughout — includes subfloor prep, underlayment/pad, moisture barrier, transitions, and grout/sealants. Tile wet areas include waterproofing and shower pan/curb where applicable. Quantities: LVT/laminate ~1,400 sf, tile ~400 sf (adjust to final selections).
1120 | Flooring material (Allowance)
Owner flooring material allowance — final selections (LVT/laminate, tile, carpet) recorded here. Selections due before the flooring phase to hold schedule and lock pricing.
1200 | Woodwork/Cabinets/Millwork
1210 | Millwork
Trim package: 5-1/2″ primed FJ baseboard; 3-1/2″ primed FJ door casing (mitered); primed FJ window sill and apron; custom closet shelving and rods. Paint-grade interior doors (6 standard styles, more available); solid-core doors at bathrooms and bedrooms. Includes door hardware (hinges, levers, stops) — finish per selection.
1220 | Finish Carpentry
Install all interior trim — baseboard, door casing, window surrounds, interior doors and hardware, stair railing/balustrade, and closet shelving/rods. Caulk and fill ready for paint.
1230 | Cabinet Specifications (Allowance)
Supply and install owner-selected cabinetry per plan — kitchen, baths, and any butler's pantry — including cabinet hardware and interior accessories. Allowance is based on preliminary plans and includes cabinets, hardware, accessories, tax, delivery, and installation. Countertops are itemized separately (1340).
1240 | Countertops (Allowance)
Hard-surface countertop allowance — kitchen, island, select bath vanities, and laundry; 3 cm quartz/granite slab. Includes templating, fabrication, edge profile, sink/cooktop cutouts, and installation. Tile backsplash included per the line item.
1300 | Appliances/Equipment
1310 | Appliance Specifications
Optional appliance allowance — dishwasher, range, and refrigerator — included when required for financing. Builder coordinates delivery and hookup (electrical/plumbing/gas connections by the respective trades). Owner-supplied appliances must be on site before trim-out.
1320 | Window Coverings (Allowance)
Allowance for window coverings — blinds or shades at windows per owner selection, measured and installed. Motorized or specialty treatments may affect the allowance.
1500 | Final Grade & Site
1510 | Final Grade & Landscaping
Final grading and rough landscaping after construction — spread stockpiled topsoil, rough-grade the lot to drain away from the house, and leave the site ready for the owner’s yard. Seeding, sod, irrigation, and plantings are by owner unless noted.

## Estimate
ESTIMATE
PO Box 516, Longview, WA 98632 • 360-200-1716
Project: Truesdell SFD Estimate EST-1001
INTERNAL — not printed
Code | Item / Description | Ext Cost | Sales Tax | Line Total | Category / Item Total | My Cost | Markup | Tax? | Allow? | Excl? | Suggested $ | Logic / basis | Sched?
0100 | General Conditions |  |  |  | 0
0110 | Permits (Allowance) |  |  |  | 0 |  |  |  | Y |  |  |  | Y
| Bldg. Permit | 0 | 0 | 0 |  | 0 | 0% | N |  | N | 8000 | Prior project basis / lump sum - confirm with sub
0120 | Electrical Utility Connections (Allowance) |  |  |  | 0 |  |  |  | Y |  |  |  | Y
| PUD Quoted install | 0 | 0 | 0 |  | 0 | 0% | N |  | N | 7500 | Prior project basis / lump sum - confirm with sub
| Gas service connection | 0 | 0 | 0 |  | 0 | 0% | N |  | N | 2500 | Allowance - gas tap/meter; confirm provider
0130 | Excavation (Allowance) |  |  |  | 0 |  |  |  | Y |  |  |  | Y
| Excavation | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 4095 | Prior project basis / lump sum - confirm with sub
| Excavation - utilities & contingency | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 3510 | Prior project basis / lump sum - confirm with sub
| Backfill - Labor | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 5850 | Prior project basis / lump sum - confirm with sub
| Backfill - Gravel and fill | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 5850 | Prior project basis / lump sum - confirm with sub
0140 | Septic system design & install (Allowance) |  |  |  | 0 |  |  |  | Y |  |  |  | Y
| Septic system install - Pressure distribution | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 14040 | Prior project basis / lump sum - confirm with sub
| Septic design | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 1404 | Prior project basis / lump sum - confirm with sub
| Septic permit | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 1170 | Prior project basis / lump sum - confirm with sub
0150 | Well setup (Allowance) |  |  |  | 0 |  |  |  | Y |  |  |  | N
| Well | 0 | 0 | 0 |  | 0 | 0% | Y |  | N | 0 | Owner-provided / allowance - set as needed
0190 | Job site services |  |  |  | 0 |  |  |  | N |  |  |  | N
| Home Cleaning @ Final | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 2925 | Prior project basis / lump sum - confirm with sub
| Portable toilet | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 1895.4 | Prior project basis / lump sum - confirm with sub
| Dumping fees / site cleanup | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 5850 | Prior project basis / lump sum - confirm with sub
0200 | Site Work |  |  |  | 0
0210 | Footing And Foundation |  |  |  | 0 |  |  |  | N |  |  |  | Y
| Foundation Labor/concrete | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 8800 | Foundation CY (perim x ht x 0.67 /27, round up 5 yd) x $440/yd
| Pump Truck | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 1872 | Prior project basis / lump sum - confirm with sub
0300 | Rough Structure |  |  |  | 0
0310 | Framing Materials (Allowance) |  |  |  | 0 |  |  |  | Y |  |  |  | Y
| Materials - 1st floor - 9.5" TJI | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 9200.8976 | From Material Takeoff: foundation & floor framing material
| Exterior Walls 9' PLT HT | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 3705.6653 | From Material Takeoff: wall framing material
| Materials - Roof pack | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 4054.0079 | From Material Takeoff: roof framing & trim material
| Materials - Trusses | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 7020 | Prior project basis / lump sum - confirm with sub
| Beams - hardware - Posts | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 1404 | Prior project basis / lump sum - confirm with sub
0320 | Framing Labor |  |  |  | 0 |  |  |  | N |  |  |  | Y
| Framing labor - living space | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 21600 | Living SF x $12/sf framing labor
| Framing labor - Covered porch/Garage | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 4680 | (Garage+porch) SF x $9/sf framing labor
0400 | Windows & Doors, Exterior |  |  |  | 0
0410 | Front Door (Allowance) |  |  |  | 0 |  |  |  | Y |  |  |  | Y
| Front door 3080 - Knotty Alder | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 5265 | Prior project basis / lump sum - confirm with sub
0420 | Other exterior doors |  |  |  | 0 |  |  |  | N |  |  |  | Y
| Exterior doors | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 1950 | Ext doors qty x $650 ea
0430 | Garage Doors |  |  |  | 0 |  |  |  | N |  |  |  | Y
| 18*8 | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 1500 | Garage doors qty x $1,500 ea
| Garage Door openers | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 450 | Garage doors qty x $450 opener ea
0440 | Windows (Allowance) |  |  |  | 0 |  |  |  | Y |  |  |  | Y
| Windows | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 6840 | Windows qty x $380 ea
| SGD (sliding glass door) | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 2200 | Sliding doors qty x $2,200 ea
0500 | Exterior Finishes |  |  |  | 0
0510 | Siding Materials |  |  |  | 0 |  |  |  | N |  |  |  | Y
| Siding materials package | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 5341.4518 | Material Takeoff siding + gable (Settings) x $5.50/sf
0520 | Siding Labor |  |  |  | 0 |  |  |  | N |  |  |  | Y
| Siding labor - 7" horizontal | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 6840 | Exterior wall + gable SF x $4/sf siding labor
| Siding labor - Soffits | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 2808 | Prior project basis / lump sum - confirm with sub
| Siding labor - Post wraps | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 1404 | Prior project basis / lump sum - confirm with sub
0530 | Roofing Specifications (Allowance) |  |  |  | 0 |  |  |  | Y |  |  |  | Y
| Roofing Material | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 13804 | Roof area (footprint x1.4) /100 sq x $425/sq material
| Roofing Labor | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 8120 | Roof squares (footprint x1.4) x $250/sq labor
0540 | Gutters |  |  |  | 0 |  |  |  | N |  |  |  | Y
| Gutters | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 1140 | Eave length ~ perimeter x $6/lf
0550 | Exterior Masonry |  |  |  | 0 |  |  |  | N |  |  |  | N
| Cultured stone | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 0 | Owner-provided / allowance - set as needed
0560 | Exterior Painting |  |  |  | 0 |  |  |  | N |  |  |  | Y
| Exterior Painting Material & Labor | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 2736 | Exterior wall + gable SF x $1.60/sf paint
0570 | Concrete Flatwork (Allowance) |  |  |  | 0 |  |  |  | Y |  |  |  | Y
| Driveway | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 3080 | Driveway length x 11 ft x $7/sf
| Exterior concrete patio & walkway | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 3600 | Exterior concrete SF x $6/sf
| Garage slab | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 2400 | Garage SF x $6/sf slab
0600 | HVAC |  |  |  | 0
0610 | HVAC |  |  |  | 0 |  |  |  | N |  |  |  | Y
| HVAC system | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 17100 | Living SF x $9.50/sf complete HVAC
0620 | Fireplace (Allowance) |  |  |  | 0 |  |  |  | Y |  |  |  | Y
| Fireplace - install only + stove pipe parts | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 5850 | Prior project basis / lump sum - confirm with sub
0700 | Plumbing |  |  |  | 0
0710 | Plumbing (Allowance) |  |  |  | 0 |  |  |  | Y |  |  |  | Y
| Plumbing quote complete | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 17550 | Living SF x $9.75/sf (or by fixture count)
0800 | Electrical |  |  |  | 0
0810 | Electrical (Allowance) |  |  |  | 0 |  |  |  | Y |  |  |  | Y
| Electrical System | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 21060 | Living SF x $11.70/sf electrical
| Low-voltage rough-in (data / cable / TV) | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 1500 | Allowance - data/cable/TV drops
| EV charger circuit (rough-in) | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 900 | Allowance - 240V EV rough-in
0820 | Electrical Fixtures (Allowance) |  |  |  | 0 |  |  |  | Y |  |  |  | N
| Fixture allowance | 0 | 0 | 0 |  | 0 | 0% | Y |  | N | 0 | Owner-provided / allowance - set as needed
0900 | Insulation |  |  |  | 0
0910 | Insulation |  |  |  | 0 |  |  |  | N |  |  |  | Y
| Insulation | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 6547.5 | Walls SFx$2.25 + ceiling(living SF)x$1.50
1000 | Interior Wall & Ceiling Finishes |  |  |  | 0
1010 | Drywall |  |  |  | 0 |  |  |  | N |  |  |  | Y
| Drywall, hang, tape, texture | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 13230 | Living SF x 3.5 (drywall area factor) x $2.10/sf
1020 | Interior Paint |  |  |  | 0 |  |  |  | N |  |  |  | Y
| Interior wall/ceiling/trim painting | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 6930 | Drywall area (livingx3.5) x $1.10/sf
1030 | Interior Paint Color(s) |  |  |  | 0 |  |  |  | N |  |  |  | N
1040 | Bathroom accessories and mirrors (Allowance) |  |  |  | 0 |  |  |  | Y |  |  |  | Y
| Bathroom mirrors | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 0 | Owner-provided / allowance - set as needed
| TP holders, towel rod, towel ring per bath | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 0 | Owner-provided / allowance - set as needed
1050 | Masonry - Fireplace facade (Allowance) |  |  |  | 0 |  |  |  | Y |  |  |  | N
| Stone | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 0 | Owner-provided / allowance - set as needed
| Wood Mantel | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 0 | Owner-provided / allowance - set as needed
1100 | Flooring |  |  |  | 0
1110 | Flooring Labor (Allowance) |  |  |  | 0 |  |  |  | Y |  |  |  | Y
| LVT/Laminate | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 3500 | Remaining floor SF x $2.50/sf LVT labor
| Tile (install) | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 4000 | Tile area SF x $10/sf labor
| Shower pan / tile waterproofing | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 1200 | Allowance per shower
| Shower glass enclosure | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 1500 | Allowance per glass enclosure
1120 | Flooring material (Allowance) |  |  |  | 0 |  |  |  | Y |  |  |  | N
| Tile Selection | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 2000 | Tile area SF x $5/sf material allowance
| LVT/Laminate | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 5600 | Remaining floor SF x $4/sf material allowance
1200 | Woodwork/Cabinets/Millwork |  |  |  | 0
1210 | Millwork |  |  |  | 0 |  |  |  | N |  |  |  | Y
| Interior trim pack | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 4500 | Living SF x $2.50/sf trim package material
1220 | Finish Carpentry |  |  |  | 0 |  |  |  | N |  |  |  | Y
| Finish labor | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 4500 | Living SF x $2.50/sf finish carpentry labor
1230 | Cabinet Specifications (Allowance) |  |  |  | 0 |  |  |  | Y |  |  |  | Y
| Supply and install cabinets complete | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 7000 | Kitchen run x $350/lf (upper+lower) + baths
1240 | Countertops (Allowance) |  |  |  | 0 |  |  |  | Y |  |  |  | Y
| Countertops - Group B | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 2730 | Kitchen run x 2.1 sf/lf x $65/sf quartz
| Backsplash - Tile | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 750 | Kitchen run x 1.5 sf/lf x $25/sf backsplash
1300 | Appliances/Equipment |  |  |  | 0
1310 | Appliance Specifications |  |  |  | 0 |  |  |  | N |  |  |  | N
| Appliance purchase - delivery - install | 0 | 0 | 0 |  | 0 | 0% | Y |  | N | 0 | Owner-provided / allowance - set as needed
1320 | Window Coverings (Allowance) |  |  |  | 0 |  |  |  | Y |  |  |  | N
| Window coverings / blinds allowance | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 3240 | Windows qty x $180 ea blinds allowance
1500 | Final Grade & Site |  |  |  | 0
1510 | Final Grade & Landscaping |  |  |  | 0 |  |  |  | N |  |  |  | Y
| Final grade and rough landscaping | 0 | 0 | 0 |  | 0 | 20% | Y |  | N | 3000 | Allowance - spread topsoil + rough grade
| TOTALS | 0 | 0 | 0 |  | Your cost | 0 |  |  |  | 330591.9226
|  |  | Ext (after markup, pre-tax) | 0 |  | Markup $ | 0
|  |  | Sales Tax | 0 |  | Margin % | —
|  |  | GRAND TOTAL | 0
|  |  | Price per sq ft | 0

## Allowances
ALLOWANCES
PO Box 516, Longview, WA 98632 • 360-200-1716
Project: Truesdell SFD Estimate EST-1001
Items toggled Allow? = Y on the Estimate. Enter the actual selected cost to track budget vs. spend.
Code | Category | Item | Allow? | Allowance $ | Actual $ | Variance | Notes
0110 | General Conditions | Permits | Y | 0
0120 | General Conditions | Electrical Utility Connections | Y | 0
0130 | General Conditions | Excavation | Y | 0
0140 | General Conditions | Septic system design & install | Y | 0
0150 | General Conditions | Well setup | Y | 0
0190 | General Conditions | Job site services | N | 0
0210 | Site Work | Footing And Foundation | N | 0
0310 | Rough Structure | Framing Materials | Y | 0
0320 | Rough Structure | Framing Labor | N | 0
0410 | Windows & Doors, Exterior | Front Door | Y | 0
0420 | Windows & Doors, Exterior | Other exterior doors | N | 0
0430 | Windows & Doors, Exterior | Garage Doors | N | 0
0440 | Windows & Doors, Exterior | Windows | Y | 0
0510 | Exterior Finishes | Siding Materials | N | 0
0520 | Exterior Finishes | Siding Labor | N | 0
0530 | Exterior Finishes | Roofing Specifications | Y | 0
0540 | Exterior Finishes | Gutters | N | 0
0550 | Exterior Finishes | Exterior Masonry | N | 0
0560 | Exterior Finishes | Exterior Painting | N | 0
0570 | Exterior Finishes | Concrete Flatwork | Y | 0
0610 | HVAC | HVAC | N | 0
0620 | HVAC | Fireplace | Y | 0
0710 | Plumbing | Plumbing | Y | 0
0810 | Electrical | Electrical | Y | 0
0820 | Electrical | Electrical Fixtures | Y | 0
0910 | Insulation | Insulation | N | 0
1010 | Interior Wall & Ceiling Finishes | Drywall | N | 0
1020 | Interior Wall & Ceiling Finishes | Interior Paint | N | 0
1030 | Interior Wall & Ceiling Finishes | Interior Paint Color(s) | N | 0
1040 | Interior Wall & Ceiling Finishes | Bathroom accessories and mirrors | Y | 0
1050 | Interior Wall & Ceiling Finishes | Masonry - Fireplace facade | Y | 0
1110 | Flooring | Flooring Labor | Y | 0
1120 | Flooring | Flooring material | Y | 0
1210 | Woodwork/Cabinets/Millwork | Millwork | N | 0
1220 | Woodwork/Cabinets/Millwork | Finish Carpentry | N | 0
1230 | Woodwork/Cabinets/Millwork | Cabinet Specifications | Y | 0
1240 | Woodwork/Cabinets/Millwork | Countertops | Y | 0
1310 | Appliances/Equipment | Appliance Specifications | N | 0
1320 | Appliances/Equipment | Window Coverings | Y | 0
1510 | Final Grade & Site | Final Grade & Landscaping | N | 0
|  | TOTAL ALLOWANCES |  | 0 | 0 | 0

## Schedule
PROJECT SCHEDULE (one line per estimate item — add the items below as each job needs them)
ID | Task | Dur | Start | Finish | Pred | Anchor | Status | % Done
1 | 0110 Permits | [5 empty] | Not Started | 0%
2 | 0120 Electrical Utility Connections | [5 empty] | Not Started | 0%
3 | 0130 Excavation | [5 empty] | Not Started | 0%
4 | 0140 Septic system design & install | [5 empty] | Not Started | 0%
5 | 0210 Footing And Foundation | [5 empty] | Not Started | 0%
6 | 0310 Framing Materials | [5 empty] | Not Started | 0%
7 | 0320 Framing Labor | [5 empty] | Not Started | 0%
8 | 0410 Front Door | [5 empty] | Not Started | 0%
9 | 0420 Other exterior doors | [5 empty] | Not Started | 0%
10 | 0430 Garage Doors | [5 empty] | Not Started | 0%
11 | 0440 Windows | [5 empty] | Not Started | 0%
12 | 0510 Siding Materials | [5 empty] | Not Started | 0%
13 | 0520 Siding Labor | [5 empty] | Not Started | 0%
14 | 0530 Roofing Specifications | [5 empty] | Not Started | 0%
15 | 0540 Gutters | [5 empty] | Not Started | 0%
16 | 0560 Exterior Painting | [5 empty] | Not Started | 0%
17 | 0570 Concrete Flatwork | [5 empty] | Not Started | 0%
18 | 0610 HVAC | [5 empty] | Not Started | 0%
19 | 0620 Fireplace | [5 empty] | Not Started | 0%
20 | 0710 Plumbing | [5 empty] | Not Started | 0%
21 | 0810 Electrical | [5 empty] | Not Started | 0%
22 | 0910 Insulation | [5 empty] | Not Started | 0%
23 | 1010 Drywall | [5 empty] | Not Started | 0%
24 | 1020 Interior Paint | [5 empty] | Not Started | 0%
25 | 1040 Bathroom accessories and mirrors | [5 empty] | Not Started | 0%
26 | 1110 Flooring Labor | [5 empty] | Not Started | 0%
27 | 1210 Millwork | [5 empty] | Not Started | 0%
28 | 1220 Finish Carpentry | [5 empty] | Not Started | 0%
29 | 1230 Cabinet Specifications | [5 empty] | Not Started | 0%
30 | 1240 Countertops | [5 empty] | Not Started | 0%
31 | 1510 Final Grade & Landscaping | [5 empty] | Not Started | 0%
Formulas:
Dur = IFERROR(NETWORKDAYS([Start],[Finish]),"")
Note on G3: Optional. Type a date to PIN this task's Start, overriding the predecessor. Leave blank to flow from Duration + Predecessor.

## Calendar
PROJECT CALENDAR (auto from the Schedule — shaded = work happening; label = task starting that day)
Week of | Mon | Tue | Wed | Thu | Fri | Sat | Sun
2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05
2026-07-06 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12
2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19
2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26
2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02
2026-08-03 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09
2026-08-10 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16
2026-08-17 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23
2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30
2026-08-31 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06
2026-09-07 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13
2026-09-14 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20
2026-09-21 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27
2026-09-28 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04
2026-10-05 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11
2026-10-12 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18
2026-10-19 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25
2026-10-26 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01
2026-11-02 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08
2026-11-09 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15
2026-11-16 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22
2026-11-23 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28 | 2026-11-29
2026-11-30 | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05 | 2026-12-06
2026-12-07 | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-12 | 2026-12-13
2026-12-14 | 2026-12-14 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-18 | 2026-12-19 | 2026-12-20
2026-12-21 | 2026-12-21 | 2026-12-22 | 2026-12-23 | 2026-12-24 | 2026-12-25 | 2026-12-26 | 2026-12-27
2026-12-28 | 2026-12-28 | 2026-12-29 | 2026-12-30 | 2026-12-31 | 2027-01-01 | 2027-01-02 | 2027-01-03
2027-01-04 | 2027-01-04 | 2027-01-05 | 2027-01-06 | 2027-01-07 | 2027-01-08 | 2027-01-09 | 2027-01-10
2027-01-11 | 2027-01-11 | 2027-01-12 | 2027-01-13 | 2027-01-14 | 2027-01-15 | 2027-01-16 | 2027-01-17
2027-01-18 | 2027-01-18 | 2027-01-19 | 2027-01-20 | 2027-01-21 | 2027-01-22 | 2027-01-23 | 2027-01-24
2027-01-25 | 2027-01-25 | 2027-01-26 | 2027-01-27 | 2027-01-28 | 2027-01-29 | 2027-01-30 | 2027-01-31
2027-02-01 | 2027-02-01 | 2027-02-02 | 2027-02-03 | 2027-02-04 | 2027-02-05 | 2027-02-06 | 2027-02-07
2027-02-08 | 2027-02-08 | 2027-02-09 | 2027-02-10 | 2027-02-11 | 2027-02-12 | 2027-02-13 | 2027-02-14
2027-02-15 | 2027-02-15 | 2027-02-16 | 2027-02-17 | 2027-02-18 | 2027-02-19 | 2027-02-20 | 2027-02-21
2027-02-22 | 2027-02-22 | 2027-02-23 | 2027-02-24 | 2027-02-25 | 2027-02-26 | 2027-02-27 | 2027-02-28
2027-03-01 | 2027-03-01 | 2027-03-02 | 2027-03-03 | 2027-03-04 | 2027-03-05 | 2027-03-06 | 2027-03-07
2027-03-08 | 2027-03-08 | 2027-03-09 | 2027-03-10 | 2027-03-11 | 2027-03-12 | 2027-03-13 | 2027-03-14
2027-03-15 | 2027-03-15 | 2027-03-16 | 2027-03-17 | 2027-03-18 | 2027-03-19 | 2027-03-20 | 2027-03-21

## Exclusions
EXCLUSIONS
PO Box 516, Longview, WA 98632 • 360-200-1716
Project: Truesdell SFD Estimate EST-1001
Lines toggled Excl? = Y on the Estimate are excluded (cost zeroed) and collected here for reference.
Item | Excluded line | Value | Excl?
Permits | Bldg. Permit | 0 | N
Electrical Utility Connections | PUD Quoted install | 0 | N
Electrical Utility Connections | Gas service connection | 0 | N
Excavation | Excavation | 0 | N
Excavation | Excavation - utilities & contingency | 0 | N
Excavation | Backfill - Labor | 0 | N
Excavation | Backfill - Gravel and fill | 0 | N
Septic system design & install | Septic system install - Pressure distribution | 0 | N
Septic system design & install | Septic design | 0 | N
Septic system design & install | Septic permit | 0 | N
Well setup | Well | 0 | N
Job site services | Home Cleaning @ Final | 0 | N
Job site services | Portable toilet | 0 | N
Job site services | Dumping fees / site cleanup | 0 | N
Footing And Foundation | Foundation Labor/concrete | 0 | N
Footing And Foundation | Pump Truck | 0 | N
Framing Materials | Materials - 1st floor - 9.5" TJI | 0 | N
Framing Materials | Exterior Walls 9' PLT HT | 0 | N
Framing Materials | Materials - Roof pack | 0 | N
Framing Materials | Materials - Trusses | 0 | N
Framing Materials | Beams - hardware - Posts | 0 | N
Framing Labor | Framing labor - living space | 0 | N
Framing Labor | Framing labor - Covered porch/Garage | 0 | N
Front Door | Front door 3080 - Knotty Alder | 0 | N
Other exterior doors | Exterior doors | 0 | N
Garage Doors | 18*8 | 0 | N
Garage Doors | Garage Door openers | 0 | N
Windows | Windows | 0 | N
Windows | SGD (sliding glass door) | 0 | N
Siding Materials | Siding materials package | 0 | N
Siding Labor | Siding labor - 7" horizontal | 0 | N
Siding Labor | Siding labor - Soffits | 0 | N
Siding Labor | Siding labor - Post wraps | 0 | N
Roofing Specifications | Roofing Material | 0 | N
Roofing Specifications | Roofing Labor | 0 | N
Gutters | Gutters | 0 | N
Exterior Masonry | Cultured stone | 0 | N
Exterior Painting | Exterior Painting Material & Labor | 0 | N
Concrete Flatwork | Driveway | 0 | N
Concrete Flatwork | Exterior concrete patio & walkway | 0 | N
Concrete Flatwork | Garage slab | 0 | N
HVAC | HVAC system | 0 | N
Fireplace | Fireplace - install only + stove pipe parts | 0 | N
Plumbing | Plumbing quote complete | 0 | N
Electrical | Electrical System | 0 | N
Electrical | Low-voltage rough-in (data / cable / TV) | 0 | N
Electrical | EV charger circuit (rough-in) | 0 | N
Electrical Fixtures | Fixture allowance | 0 | N
Insulation | Insulation | 0 | N
Drywall | Drywall, hang, tape, texture | 0 | N
Interior Paint | Interior wall/ceiling/trim painting | 0 | N
Bathroom accessories and mirrors | Bathroom mirrors | 0 | N
Bathroom accessories and mirrors | TP holders, towel rod, towel ring per bath | 0 | N
Masonry - Fireplace facade | Stone | 0 | N
Masonry - Fireplace facade | Wood Mantel | 0 | N
Flooring Labor | LVT/Laminate | 0 | N
Flooring Labor | Tile (install) | 0 | N
Flooring Labor | Shower pan / tile waterproofing | 0 | N
Flooring Labor | Shower glass enclosure | 0 | N
Flooring material | Tile Selection | 0 | N
Flooring material | LVT/Laminate | 0 | N
Millwork | Interior trim pack | 0 | N
Finish Carpentry | Finish labor | 0 | N
Cabinet Specifications | Supply and install cabinets complete | 0 | N
Countertops | Countertops - Group B | 0 | N
Countertops | Backsplash - Tile | 0 | N
Appliance Specifications | Appliance purchase - delivery - install | 0 | N
Window Coverings | Window coverings / blinds allowance | 0 | N
Final Grade & Landscaping | Final grade and rough landscaping | 0 | N
| TOTAL EXCLUDED VALUE | 0

## Draws
DRAW SCHEDULE
PO Box 516, Longview, WA 98632 • 360-200-1716
Project: Truesdell SFD
Code | Item / Description | Contract | Draw 1 | Draw 2 | Draw 3 | Draw 4 | Draw 5 | Final Draw | Total Drawn | Remaining | % Billed
0100 | General Conditions | 0 | [6 empty] | 0 | 0 | 0%
0110 | Permits | 0 | [6 empty] | 0 | 0 | 0%
| Bldg. Permit | 0 | [6 empty] | 0 | 0 | 0%
0120 | Electrical Utility Connections | 0 | [6 empty] | 0 | 0 | 0%
| PUD Quoted install | 0 | [6 empty] | 0 | 0 | 0%
| Gas service connection | 0 | [6 empty] | 0 | 0 | 0%
0130 | Excavation | 0 | [6 empty] | 0 | 0 | 0%
| Excavation | 0 | [6 empty] | 0 | 0 | 0%
| Excavation - utilities & contingency | 0 | [6 empty] | 0 | 0 | 0%
| Backfill - Labor | 0 | [6 empty] | 0 | 0 | 0%
| Backfill - Gravel and fill | 0 | [6 empty] | 0 | 0 | 0%
0140 | Septic system design & install | 0 | [6 empty] | 0 | 0 | 0%
| Septic system install - Pressure distribution | 0 | [6 empty] | 0 | 0 | 0%
| Septic design | 0 | [6 empty] | 0 | 0 | 0%
| Septic permit | 0 | [6 empty] | 0 | 0 | 0%
0150 | Well setup | 0 | [6 empty] | 0 | 0 | 0%
| Well | 0 | [6 empty] | 0 | 0 | 0%
0190 | Job site services | 0 | [6 empty] | 0 | 0 | 0%
| Home Cleaning @ Final | 0 | [6 empty] | 0 | 0 | 0%
| Portable toilet | 0 | [6 empty] | 0 | 0 | 0%
| Dumping fees / site cleanup | 0 | [6 empty] | 0 | 0 | 0%
0200 | Site Work | 0 | [6 empty] | 0 | 0 | 0%
0210 | Footing And Foundation | 0 | [6 empty] | 0 | 0 | 0%
| Foundation Labor/concrete | 0 | [6 empty] | 0 | 0 | 0%
| Pump Truck | 0 | [6 empty] | 0 | 0 | 0%
0300 | Rough Structure | 0 | [6 empty] | 0 | 0 | 0%
0310 | Framing Materials | 0 | [6 empty] | 0 | 0 | 0%
| Materials - 1st floor - 9.5" TJI | 0 | [6 empty] | 0 | 0 | 0%
| Exterior Walls 9' PLT HT | 0 | [6 empty] | 0 | 0 | 0%
| Materials - Roof pack | 0 | [6 empty] | 0 | 0 | 0%
| Materials - Trusses | 0 | [6 empty] | 0 | 0 | 0%
| Beams - hardware - Posts | 0 | [6 empty] | 0 | 0 | 0%
0320 | Framing Labor | 0 | [6 empty] | 0 | 0 | 0%
| Framing labor - living space | 0 | [6 empty] | 0 | 0 | 0%
| Framing labor - Covered porch/Garage | 0 | [6 empty] | 0 | 0 | 0%
0400 | Windows & Doors, Exterior | 0 | [6 empty] | 0 | 0 | 0%
0410 | Front Door | 0 | [6 empty] | 0 | 0 | 0%
| Front door 3080 - Knotty Alder | 0 | [6 empty] | 0 | 0 | 0%
0420 | Other exterior doors | 0 | [6 empty] | 0 | 0 | 0%
| Exterior doors | 0 | [6 empty] | 0 | 0 | 0%
0430 | Garage Doors | 0 | [6 empty] | 0 | 0 | 0%
| 18*8 | 0 | [6 empty] | 0 | 0 | 0%
| Garage Door openers | 0 | [6 empty] | 0 | 0 | 0%
0440 | Windows | 0 | [6 empty] | 0 | 0 | 0%
| Windows | 0 | [6 empty] | 0 | 0 | 0%
| SGD (sliding glass door) | 0 | [6 empty] | 0 | 0 | 0%
0500 | Exterior Finishes | 0 | [6 empty] | 0 | 0 | 0%
0510 | Siding Materials | 0 | [6 empty] | 0 | 0 | 0%
| Siding materials package | 0 | [6 empty] | 0 | 0 | 0%
0520 | Siding Labor | 0 | [6 empty] | 0 | 0 | 0%
| Siding labor - 7" horizontal | 0 | [6 empty] | 0 | 0 | 0%
| Siding labor - Soffits | 0 | [6 empty] | 0 | 0 | 0%
| Siding labor - Post wraps | 0 | [6 empty] | 0 | 0 | 0%
0530 | Roofing Specifications | 0 | [6 empty] | 0 | 0 | 0%
| Roofing Material | 0 | [6 empty] | 0 | 0 | 0%
| Roofing Labor | 0 | [6 empty] | 0 | 0 | 0%
0540 | Gutters | 0 | [6 empty] | 0 | 0 | 0%
| Gutters | 0 | [6 empty] | 0 | 0 | 0%
0550 | Exterior Masonry | 0 | [6 empty] | 0 | 0 | 0%
| Cultured stone | 0 | [6 empty] | 0 | 0 | 0%
0560 | Exterior Painting | 0 | [6 empty] | 0 | 0 | 0%
| Exterior Painting Material & Labor | 0 | [6 empty] | 0 | 0 | 0%
0570 | Concrete Flatwork | 0 | [6 empty] | 0 | 0 | 0%
| Driveway | 0 | [6 empty] | 0 | 0 | 0%
| Exterior concrete patio & walkway | 0 | [6 empty] | 0 | 0 | 0%
| Garage slab | 0 | [6 empty] | 0 | 0 | 0%
0600 | HVAC | 0 | [6 empty] | 0 | 0 | 0%
0610 | HVAC | 0 | [6 empty] | 0 | 0 | 0%
| HVAC system | 0 | [6 empty] | 0 | 0 | 0%
0620 | Fireplace | 0 | [6 empty] | 0 | 0 | 0%
| Fireplace - install only + stove pipe parts | 0 | [6 empty] | 0 | 0 | 0%
0700 | Plumbing | 0 | [6 empty] | 0 | 0 | 0%
0710 | Plumbing | 0 | [6 empty] | 0 | 0 | 0%
| Plumbing quote complete | 0 | [6 empty] | 0 | 0 | 0%
0800 | Electrical | 0 | [6 empty] | 0 | 0 | 0%
0810 | Electrical | 0 | [6 empty] | 0 | 0 | 0%
| Electrical System | 0 | [6 empty] | 0 | 0 | 0%
| Low-voltage rough-in (data / cable / TV) | 0 | [6 empty] | 0 | 0 | 0%
| EV charger circuit (rough-in) | 0 | [6 empty] | 0 | 0 | 0%
0820 | Electrical Fixtures | 0 | [6 empty] | 0 | 0 | 0%
| Fixture allowance | 0 | [6 empty] | 0 | 0 | 0%
0900 | Insulation | 0 | [6 empty] | 0 | 0 | 0%
0910 | Insulation | 0 | [6 empty] | 0 | 0 | 0%
| Insulation | 0 | [6 empty] | 0 | 0 | 0%
1000 | Interior Wall & Ceiling Finishes | 0 | [6 empty] | 0 | 0 | 0%
1010 | Drywall | 0 | [6 empty] | 0 | 0 | 0%
| Drywall, hang, tape, texture | 0 | [6 empty] | 0 | 0 | 0%
1020 | Interior Paint | 0 | [6 empty] | 0 | 0 | 0%
| Interior wall/ceiling/trim painting | 0 | [6 empty] | 0 | 0 | 0%
1030 | Interior Paint Color(s) | 0 | [6 empty] | 0 | 0 | 0%
1040 | Bathroom accessories and mirrors | 0 | [6 empty] | 0 | 0 | 0%
| Bathroom mirrors | 0 | [6 empty] | 0 | 0 | 0%
| TP holders, towel rod, towel ring per bath | 0 | [6 empty] | 0 | 0 | 0%
1050 | Masonry - Fireplace facade | 0 | [6 empty] | 0 | 0 | 0%
| Stone | 0 | [6 empty] | 0 | 0 | 0%
| Wood Mantel | 0 | [6 empty] | 0 | 0 | 0%
1100 | Flooring | 0 | [6 empty] | 0 | 0 | 0%
1110 | Flooring Labor | 0 | [6 empty] | 0 | 0 | 0%
| LVT/Laminate | 0 | [6 empty] | 0 | 0 | 0%
| Tile (install) | 0 | [6 empty] | 0 | 0 | 0%
| Shower pan / tile waterproofing | 0 | [6 empty] | 0 | 0 | 0%
| Shower glass enclosure | 0 | [6 empty] | 0 | 0 | 0%
1120 | Flooring material | 0 | [6 empty] | 0 | 0 | 0%
| Tile Selection | 0 | [6 empty] | 0 | 0 | 0%
| LVT/Laminate | 0 | [6 empty] | 0 | 0 | 0%
1200 | Woodwork/Cabinets/Millwork | 0 | [6 empty] | 0 | 0 | 0%
1210 | Millwork | 0 | [6 empty] | 0 | 0 | 0%
| Interior trim pack | 0 | [6 empty] | 0 | 0 | 0%
1220 | Finish Carpentry | 0 | [6 empty] | 0 | 0 | 0%
| Finish labor | 0 | [6 empty] | 0 | 0 | 0%
1230 | Cabinet Specifications | 0 | [6 empty] | 0 | 0 | 0%
| Supply and install cabinets complete | 0 | [6 empty] | 0 | 0 | 0%
1240 | Countertops | 0 | [6 empty] | 0 | 0 | 0%
| Countertops - Group B | 0 | [6 empty] | 0 | 0 | 0%
| Backsplash - Tile | 0 | [6 empty] | 0 | 0 | 0%
1300 | Appliances/Equipment | 0 | [6 empty] | 0 | 0 | 0%
1310 | Appliance Specifications | 0 | [6 empty] | 0 | 0 | 0%
| Appliance purchase - delivery - install | 0 | [6 empty] | 0 | 0 | 0%
1320 | Window Coverings | 0 | [6 empty] | 0 | 0 | 0%
| Window coverings / blinds allowance | 0 | [6 empty] | 0 | 0 | 0%
1500 | Final Grade & Site | 0 | [6 empty] | 0 | 0 | 0%
1510 | Final Grade & Landscaping | 0 | [6 empty] | 0 | 0 | 0%
| Final grade and rough landscaping | 0 | [6 empty] | 0 | 0 | 0%
|  | 0 | [6 empty] | 0 | 0 | 0%
| TOTALS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Draw date:
CHANGE ORDERS |  |  |  | PROJECT FINANCE
# | Description | Amount |  | Original Contract |  |  |  |  | 0
CO1 |  |  |  | Change Orders (+) |  |  |  |  | 0
CO2 |  |  |  | Adjusted Contract |  |  |  |  | 0
CO3 |  |  |  | Total Drawn to date |  |  |  |  | 0
CO4 |  |  |  | Paid by Owner Direct
CO5 |  |  |  | Remaining Balance |  |  |  |  | 0
CO6
CO7
CO8
| Change Order Total | 0
APPROVALS & ACKNOWLEDGEMENT
Contractor — Ridgeline Construction | [6 empty] | Date:
|  | Signature | [5 empty] | Date
Owner / Client | [6 empty] | Date:
|  | Signature | [5 empty] | Date
Lender / Inspector (if required) | [6 empty] | Date:
|  | Signature | [5 empty] | Date

## Material Takeoff
RIDGELINE CONSTRUCTION
MATERIAL LIST - No pricing on this tab ¦ Col H shows formula logic (excluded from print)
JOB INFORMATION |  |  |  |  | KEY DIMENSIONS (yellow = enter here)
Job Name: | Truesdell SFD |  |  |  | Ext. Wall Lineal Ft: | 190
Client Name: |  |  |  |  | Ext. Wall Sq Ft: | 1710
Job Address: | 0 |  |  |  | Roof Sq Ft: | 3248
Date: | 2026-07-02 |  |  |  | Living Sq Ft: | 1800
Estimator: |  |  |  |  | Deck Sq Ft: | 0
[5 empty] | Concrete Slab Sq Ft: | 400
# | Description | Size | Grade / Species | Use / Location / Notes | Qty | Unit | Formula Logic [screen only]
FOUNDATION & FLOOR STRUCTURE
1 | PT sill plate | 2x6 16' | P.T. pine | Foundation perimeter sill | 12 | pcs | EWLF / 16' each
2 | Sill seal foam | 6in 50' | foam/fiberglass | Between sill & concrete | 4 | rolls | EWLF / 50' per roll
3 | Sill plate washers | 3x3x1/4in | galvanized | Under anchor bolt nuts | 4 | boxes | EWLF x 2 / 100 per box
4 | BCI floor joist pkg | 9-1/2in BCI-5000 | engineered | Floor joists 16" o.c. | 1440 | LF | LSF x 0.80 LF
5 | T&G OSB subfloor | 4x8 1-1/8in | OSB T&G | Glue-nail subfloor | 60 | sheets | LSF x 1.05 / 32 sf/sheet
6 | Pony wall plate | 2x6 16' | KD DF | Pony wall top & bottom plates | 24 | pcs | EWLF x 2 plates / 16'
7 | Pony wall stud | 2x6 104-5/8in | KD DF | Pony wall studs 16" o.c. | 143 | pcs | EWLF x 0.75 studs
8 | Pony wall sheathing | 4x8 7/16in | OSB RTD | Pony wall ext sheathing | 12 | sheets | EWLF x 2 sides / 32 sf/sheet
9 | Framing nails | 3in 10d | vinyl coated | Framing nailer | 4 | boxes | (EWSF + LSF + RSF) / 2000 per box
10 | Sheathing nails | 2-3/8in 8d | ring-shank galv | Sheathing nailer | 3 | boxes | (EWSF + RSF) / 2000 per box
11 | Sheathing staples | 1-3/4in 7/16in | electro galv | Sheathing stapler | 1 | boxes | EWSF / 2000
WALL FRAMING
12 | Ext wall plate | 2x6 16' | KD DF | Ext walls - 3 plates + window cuts & backing | 45 | pcs | EWLF x 3 plates / 16' x 1.25 (incl. window cut waste & backing)
13 | Ext wall stud | 2x6 104-5/8in | KD DF | Ext studs 16" o.c. | 164 | pcs | EWSF / 9 sf x 0.75 x 1.15 waste
14 | Wall sheathing | 4x9 7/16in | OSB RTD | Ext wall sheathing | 53 | sheets | EWSF x 1.10 / 36 sf/sheet
15 | Window header | 4x10 14' | #2 DF GRN | Window rough openings | 0 | pcs | MANUAL
16 | LG door/garage header | Glulam 5-1/2x12 | 1.8E DF | Garage or large openings | 0 | LF | MANUAL
17 | Int wall plate | 2x4 16' | KD DF | Int walls - 3 plates + 10% waste | 47 | pcs | LSF / 8 x 3 plates / 16' x 1.10
18 | Int wall stud | 2x4 104-5/8in | KD DF | Int studs 16" o.c. | 195 | pcs | LSF / 8 x 0.75 x 1.15 waste
19 | PT sill (garage/slab) | 2x4 14' | P.T. pine | Interior slab sill plate | 0 | pcs | MANUAL
ROOF FRAMING & TRIM
20 | Roof sheathing | 4x8 7/16in | OSB RTD | Roof decking | 112 | sheets | RSF x 1.10 / 32 sf/sheet
21 | Plywood clips | 7/16in H-clips | metal | Between roof sheets at mid-span | 51 | boxes | RSF / 64 sf per box
22 | Barge rafter | 2x8 20' | primed cypress | Barge rafters & gable | 3 | pcs | EWLF x 0.20 / 20' x 1.10
23 | Fascia board | 5/4x8 20' | primed cypress | Fascia | 10 | pcs | EWLF x 1.05 / 20'
24 | Subfascia nailer | 1x4 12' | utility DF | Subfascia | 17 | pcs | EWLF x 1.05 / 12'
25 | Roof bracing/lookout | 2x4 12' | KD DF | Outlookers, bracing | 3 | pcs | EWLF x 0.15 / 12'
26 | Soffit panel | 16inx16ft 7/16in | LP SmartSide | Eave soffit | 18 | pcs | EWLF x 1.5 ft overhang / 16'
27 | Barge sheathing | 12inx16ft 7/16in | LP SmartSide | Barge rafter sheathing | 2 | pcs | EWLF x 0.15 / 16'
28 | Barge trim | 1x4 20' | primed cypress | Barge rafter trim cover | 2 | pcs | EWLF x 0.20 / 20'
SIDING & EXTERIOR TRIM
29 | House wrap | 9ftx150ft | Tyvek HomeWrap | Full exterior wrap | 2 | rolls | EWSF / 1350 sf per roll
30 | Flashing tape 6in | 6in roll | butyl | Window/door RO flashing | 4 | rolls | EWLF / 50' per roll
31 | Flashing tape 4in | 4in roll | butyl | Seams & penetrations | 4 | rolls | EWLF / 50' per roll
32 | Tyvek tape | 2in roll | Tyvek tape | Sealing wrap seams | 4 | rolls | EWSF / 500 per roll
33 | Lap siding Hz10 | 8-1/4inx12ft | fiber cement | Exterior lap siding | 19 | squares | EWSF x 1.10 / 100 sf per sq
34 | Corner boards | 5/4x4 20' | primed cypress | Exterior corners | 12 | pcs | EWLF x 0.06 (corner count est.)
35 | Window casing trim | 5/4x4 16' | primed cypress | Window casings | 0 | pcs | MANUAL
36 | Band/trim board | 5/4x6 20' | primed cypress | Band boards, trim | 2 | pcs | EWLF x 0.15 / 20'
37 | Belly band | 5/4x8 16' | primed cypress | Belly band / water table | 13 | pcs | EWLF x 1.05 / 16'
38 | Inside corners | 2x2 10' | primed | Inside corner trim | 8 | pcs | EWLF x 0.04
39 | 1x2 trim | 1x2 16' | primed cypress | Z-flashing base / small trim | 3 | pcs | EWLF x 0.20 / 16'
40 | Hardi panel (gable) | 4x8 1/4in | cedar mill | Panel siding - gables/accents | 0 | sheets | MANUAL
41 | Window high-back flashing | 1x4in | white | Window sill pan flashing | 0 | pcs | MANUAL
42 | Exterior caulk TX-1 | 10 oz tube | sealant | All exterior joints | 9 | tubes | EWSF / 200 per tube
43 | Siding nails | electro-galv coil | fiber cement | Lap siding gun nails | 4 | boxes | EWSF / 500 per box
DECK
44 | PT ledger & rim board | 2x6 16' | P.T. | Perimeter ledger + rim | 0 | pcs | IF DSF>0: sqrt(DSF) x 3 / 16'
45 | PT deck joist | 2x8 16' | P.T. | Deck joists 16" o.c. | 0 | LF | IF DSF>0: DSF x 0.80 LF
46 | PT post 4x4 | 4x4 12' | P.T. | Deck support posts | 0 | pcs | IF DSF>0: sqrt(DSF) / 6
47 | PT beam post 6x6 | 6x6 12' | P.T. | Heavy beam support posts | 0 | pcs | IF DSF>0: 4 pcs
48 | Composite decking | 5/4x6 16' | Fiberon/Trex | Deck surface | 0 | pcs | IF DSF>0: DSF x 1.10 / (5.5/12 x 16')
49 | Deck hardware & fasteners | misc | galvanized | Joist hangers, lag screws, clips | 0 | allow | IF DSF>0: 1 allowance
STAIRCASE MATERIALS (key in qtys if applicable)
50 | Stringers | 2x12x20' | #2 DF / key in species | Staircase stringers | 0 | pcs | MANUAL -- enter qty if staircase applies
51 | Risers | varies / key in | key in | Staircase risers | 0 | pcs | MANUAL -- enter qty if staircase applies
52 | Treads | varies / key in | key in | Staircase treads | 0 | pcs | MANUAL -- enter qty if staircase applies
53 | Stair hangers & fasteners | misc | galvanized | Staircase hardware allowance | 0 | allow | MANUAL -- enter qty if staircase applies
NOTES -- Porch Posts / Beams / Other Specialty Items (type notes in yellow cells)
Porch Posts / Columns:
Beams / Specialty Framing:
Other Specialty Items:
YELLOW = enter manually ¦ All other qty auto-calculated from key dimensions ¦ Col H = formula logic (print-excluded)

## Material Estimate
RIDGELINE CONSTRUCTION - PROJECT ESTIMATE
Truesdell SFD |  |  | 0
Prices linked to Price Database (BFS QT# 4269124 - 06-26-2026) |  |  |  |  | Markup %: |  | 20%
# | Description | Size / Grade | Qty | Unit | Used / Location | Unit Price | Total
FOUNDATION & FLOOR STRUCTURE
1 | PT sill plate | 2x6 16' - P.T. pine | 12 | pcs | Foundation perimeter sill | 21.808 | 261.696
2 | Sill seal foam | 6in 50' - foam/fiberglass | 4 | rolls | Between sill & concrete | 14.95 | 59.8
3 | Sill plate washers | 3x3x1/4in - galvanized | 4 | boxes | Under anchor bolt nuts | 24.99 | 99.96
4 | BCI floor joist pkg | 9-1/2in BCI-5000 - engineered | 1440 | LF | Floor joists 16" o.c. | 3.19 | 4593.6
5 | T&G OSB subfloor | 4x8 1-1/8in - OSB T&G | 60 | sheets | Glue-nail subfloor | 38.24 | 2294.4
6 | Pony wall plate | 2x6 16' - KD DF | 24 | pcs | Pony wall top & bottom plates | 12.8 | 307.2
7 | Pony wall stud | 2x6 104-5/8in - KD DF | 143 | pcs | Pony wall studs 16" o.c. | 6.8704 | 982.4636
8 | Pony wall sheathing | 4x8 7/16in - OSB RTD | 12 | sheets | Pony wall ext sheathing | 11.904 | 142.848
9 | Framing nails | 3in 10d - vinyl coated | 4 | boxes | Framing nailer | 64.99 | 259.96
10 | Sheathing nails | 2-3/8in 8d - ring-shank galv | 3 | boxes | Sheathing nailer | 48.99 | 146.97
11 | Sheathing staples | 1-3/4in 7/16in - electro galv | 1 | boxes | Sheathing stapler | 52 | 52
FOUNDATION & FLOOR STRUCTURE — Subtotal | [6 empty] | 9200.8976
WALL FRAMING
12 | Ext wall plate | 2x6 16' - KD DF | 45 | pcs | Ext walls - 3 plates + window cuts & backing | 12.8 | 576
13 | Ext wall stud | 2x6 104-5/8in - KD DF | 164 | pcs | Ext studs 16" o.c. | 6.8704 | 1126.7415
14 | Wall sheathing | 4x9 7/16in - OSB RTD | 53 | sheets | Ext wall sheathing | 14.94 | 791.82
15 | Window header | 4x10 14' - #2 DF GRN | 0 | pcs | Window rough openings | 46.62 | 0
16 | LG door/garage header | Glulam 5-1/2x12 - 1.8E DF | 0 | LF | Garage or large openings | 22.29 | 0
17 | Int wall plate | 2x4 16' - KD DF | 47 | pcs | Int walls - 3 plates + 10% waste | 7.9467 | 373.4935
18 | Int wall stud | 2x4 104-5/8in - KD DF | 195 | pcs | Int studs 16" o.c. | 4.2954 | 837.6103
19 | PT sill (garage/slab) | 2x4 14' - P.T. pine | 0 | pcs | Interior slab sill plate | 12.7213 | 0
WALL FRAMING — Subtotal | [6 empty] | 3705.6653
ROOF FRAMING & TRIM
20 | Roof sheathing | 4x8 7/16in - OSB RTD | 112 | sheets | Roof decking | 11.904 | 1333.248
21 | Plywood clips | 7/16in H-clips - metal | 51 | boxes | Between roof sheets at mid-span | 15 | 765
22 | Barge rafter | 2x8 20' - primed cypress | 3 | pcs | Barge rafters & gable | 104.24 | 312.72
23 | Fascia board | 5/4x8 20' - primed cypress | 10 | pcs | Fascia | 76.15 | 761.5
24 | Subfascia nailer | 1x4 12' - utility DF | 17 | pcs | Subfascia | 7.5 | 127.5
25 | Roof bracing/lookout | 2x4 12' - KD DF | 3 | pcs | Outlookers, bracing | 5.96 | 17.88
26 | Soffit panel | 16inx16ft 7/16in - LP SmartSide | 18 | pcs | Eave soffit | 34.99 | 629.82
27 | Barge sheathing | 12inx16ft 7/16in - LP SmartSide | 2 | pcs | Barge rafter sheathing | 27.99 | 55.98
28 | Barge trim | 1x4 20' - primed cypress | 2 | pcs | Barge rafter trim cover | 25.1799 | 50.3599
ROOF FRAMING & TRIM — Subtotal | [6 empty] | 4054.0079
SIDING & EXTERIOR TRIM
29 | House wrap | 9ftx150ft - Tyvek HomeWrap | 2 | rolls | Full exterior wrap | 209.99 | 419.98
30 | Flashing tape 6in | 6in roll - butyl | 4 | rolls | Window/door RO flashing | 21.99 | 87.96
31 | Flashing tape 4in | 4in roll - butyl | 4 | rolls | Seams & penetrations | 17.99 | 71.96
32 | Tyvek tape | 2in roll - Tyvek tape | 4 | rolls | Sealing wrap seams | 8.49 | 33.96
33 | Lap siding Hz10 | 8-1/4inx12ft - fiber cement | 19 | squares | Exterior lap siding | 156.6 | 2975.4
34 | Corner boards | 5/4x4 20' - primed cypress | 12 | pcs | Exterior corners | 36.1001 | 433.2008
35 | Window casing trim | 5/4x4 16' - primed cypress | 0 | pcs | Window casings | 28.8801 | 0
36 | Band/trim board | 5/4x6 20' - primed cypress | 2 | pcs | Band boards, trim | 57.1125 | 114.225
37 | Belly band | 5/4x8 16' - primed cypress | 13 | pcs | Belly band / water table | 60.92 | 791.96
38 | Inside corners | 2x2 10' - primed | 8 | pcs | Inside corner trim | 7.99 | 63.92
39 | 1x2 trim | 1x2 16' - primed cypress | 3 | pcs | Z-flashing base / small trim | 10.072 | 30.216
40 | Hardi panel (gable) | 4x8 1/4in - cedar mill | 0 | sheets | Panel siding - gables/accents | 50.624 | 0
41 | Window high-back flashing | 1x4in - white | 0 | pcs | Window sill pan flashing | 14.99 | 0
42 | Exterior caulk TX-1 | 10 oz tube - sealant | 9 | tubes | All exterior joints | 5.19 | 46.71
43 | Siding nails | electro-galv coil - fiber cement | 4 | boxes | Lap siding gun nails | 67.99 | 271.96
SIDING & EXTERIOR TRIM — Subtotal | [6 empty] | 5341.4518
DECK
44 | PT ledger & rim board | 2x6 16' - P.T. | 0 | pcs | Perimeter ledger + rim | 21.808 | 0
45 | PT deck joist | 2x8 16' - P.T. | 0 | LF | Deck joists 16" o.c. | 1.684 | 0
46 | PT post 4x4 | 4x4 12' - P.T. | 0 | pcs | Deck support posts | 26.752 | 0
47 | PT beam post 6x6 | 6x6 12' - P.T. | 0 | pcs | Heavy beam support posts | 67.788 | 0
48 | Composite decking | 5/4x6 16' - Fiberon/Trex | 0 | pcs | Deck surface | 54.99 | 0
49 | Deck hardware & fasteners | misc - galvanized | 0 | allow | Joist hangers, lag screws, clips | 249.99 | 0
DECK — Subtotal | [6 empty] | 0
STAIRCASE MATERIALS (key in qtys if applicable)
50 | Stringers | 2x12x20' - #2 DF / key in species | 0 | pcs | Staircase stringers | 0 | 0
51 | Risers | varies / key in - key in | 0 | pcs | Staircase risers | 0 | 0
52 | Treads | varies / key in - key in | 0 | pcs | Staircase treads | 0 | 0
53 | Stair hangers & fasteners | misc - galvanized | 0 | allow | Staircase hardware allowance | 0 | 0
STAIRCASE MATERIALS — Subtotal | [6 empty] | 0
MATERIAL SUBTOTAL | [6 empty] | 22302.0226
SPECIAL ITEMS & ADD-ONS - Enter description, qty, and unit price in yellow cells
# | Description | Notes | Qty | Unit | Used / Location | Unit Price | Total
0
0
0
0
0
0
0
0
0
0
0
0
0
0
ADD-ONS SUBTOTAL | [6 empty] | 0
GRAND TOTAL (materials + add-ons) | [6 empty] | 22302.0226
TOTAL WITH MARKUP | [6 empty] | 26762.4271
BLUE = hardcoded ¦ GREEN = live from Price Database (BFS) ¦ YELLOW = enter manually

## Calculators
RIDGELINE CONSTRUCTION - ESTIMATING CALCULATORS
Standalone calculators - enter dimensions in yellow cells - prices pull from Price Database tab
1. DECK ESTIMATOR
INPUTS (enter in yellow) |  | RESULTS (auto)
Deck length (ft): | 0 | Deck area (sq ft): | 0
Deck width (ft): | 0 | Decking pieces: | 0
Railing LF (approx): | 0 | Joist LF needed: | 0
|  | Ledger/rim pcs (16'): | 0
-- Deck Material Pricing -- |  | Railing LF: | 0
Composite decking / pc: | 54.99 |  | None
PT 2x8 joist / LF: | 1.684 | Decking cost: | 0
Deck hardware allow $: | 0 | Joist cost: | 0
|  | Hardware: | 0
-- Metal Post & Rail System (key in qtys) -- |  |  | None
Corner posts (qty): | 0 | Corner posts cost: | 0
Mid posts (qty): | 0 | Mid posts cost: | 0
End posts (qty): | 0 | End posts cost: | 0
Stair posts (qty): | 0 | Stair posts cost: | 0
6-ft rail sections (qty): | 0 | 6-ft rail cost: | 0
8-ft rail sections (qty): | 0 | 8-ft rail cost: | 0
Brackets (qty): | 0 | Brackets cost: | 0
Lag bolts (qty): | 0 | Lag bolts cost: | 0
Misc metal rail allow $: | 0 | Misc metal allow: | 0
|  | Metal rail subtotal: | 0
-- Metal Rail Unit Pricing -- |  |  | None
Corner post / ea: | 85 | ESTIMATED TOTAL: | 0
Mid post / ea: | 75
End post / ea: | 75
Stair post / ea: | 85
6-ft rail section / ea: | 45
8-ft rail section / ea: | 55
Bracket / ea: | 8
Lag bolt / ea: | 1.25
2. METAL ROOFING ESTIMATOR
INPUTS (enter in yellow) |  | RESULTS (auto)
Roof length / ridge (ft): | 0 | Total roof area (sq ft): | 0
Slope length - peak to gutter (ft): | 0 | Squares needed (10% waste): | 0
Number of slopes: | 2 | Panels across ridge: | 0
Panel width (inches): | 16 | Total panel pieces: | 0
Ridge cap LF: | 0 | Panel length each (ft): | 0
Eave drip edge LF: | 0 | Gable trim LF (auto): | 0
Valley LF: | 0 | (slope length x 2 sides) | None
|  | Ridge cap LF: | 0
Metal panel (per sq): | 394 | Eave drip edge LF: | 0
Ridge cap (per LF): | 25 | Valley LF: | 0
Gable trim (per LF): | 25 |  | None
Eave drip edge (per LF): | 15 | Panel cost: | 0
Valley flashing (per LF): | 22 | Ridge cap cost: | 0
Fasteners allowance $: | 120 | Gable trim cost: | 0
|  | Eave drip edge cost: | 0
|  | Valley cost: | 0
|  | Fasteners: | 120
|  | ESTIMATED TOTAL: | 120
3. LAP SIDING ESTIMATOR (Hardi Hz10 8-1/4")
INPUTS (enter in yellow) |  | RESULTS (auto)
Gross wall area (sq ft): | 0 | Net siding area (sq ft): | 0
Window/door deduct (sq ft): | 0 | Hardi squares needed: | 0
Waste factor (%): | 10% | Corner boards: | 0
Wall perimeter (LF): | 0 | Tyvek rolls: | 0
|  | Caulk tubes: | 0
Hardi lap / sq: | 156.6 | Nail boxes: | 0
Corner board 5/4x4 20' / pc: | 36.1001 |  | None
Tyvek roll: | 209.99 | Siding cost: | 0
Caulk tube: | 5.19 | Corner board cost: | 0
Siding nail box: | 67.99 | Tyvek cost: | 0
|  | Caulk cost: | 0
|  | Nails cost: | 0
|  | ESTIMATED TOTAL: | 0
4. BOARD & BATTEN SIDING ESTIMATOR
INPUTS (enter in yellow) |  | RESULTS (auto)
Gross wall area (sq ft): | 0 | Net wall area (sq ft): | 0
Window/door deduct (sq ft): | 0 | Hardi 4x10 panels: | 0
Waste factor (%): | 10% | Batten LF needed: | 0
Wall height (ft): | 9 | Tyvek rolls: | 0
Batten spacing (in): | 12 | Caulk tubes: | 0
|  | Nail boxes: | 0
Hardi 4x10 panel / sheet: | 63.28 |  | None
1x3 batten (per LF): | 1.25 | Panel cost: | 0
Tyvek roll: | 209.99 | Batten cost: | 0
Caulk tube: | 5.19 | Tyvek cost: | 0
Nail box: | 67.99 | Caulk cost: | 0
|  | Nails cost: | 0
|  | ESTIMATED TOTAL: | 0

## Price Database
RIDGELINE CONSTRUCTION — MATERIAL PRICE DATABASE
BFS QT# 4269124 ¦ Date: 06-26-2026 ¦ Expires: 07-02-2026 ¦ Location: Woodland WA Yard ¦ BLUE cells = update prices here
# | Description | Item Code | Unit | Unit Price | Old Price | Change % | Notes
DIMENSIONAL LUMBER
1 | 2X6-16' #2&BTR Douglas Fir | 2616DF2 | MBF | 800 | 657 | 21.77% | General framing
2 | 2X4-16' STD&BTR Douglas Fir | 2416DF | MBF | 745 | 555 | 34.23% | General framing
3 | 2X4-104-5/8" Stud DF PET | 2410458DF | MBF | 739 | 573 | 28.97% | Precut stud - 9' wall
4 | 2X6-104-5/8" Stud DF PET | 2610458DF | MBF | 788 | 681 | 15.71% | Precut stud - 9' wall
5 | 4X10-14' #2 DF GRN | 41014GDF2 | MBF | 999 | 858 | 16.43% | Header / beam
SHEATHING & OSB
6 | 7/16"x4x8 OSB RTD | 716OSB | MSF | 372 | 456 | -18.42% | Wall sheathing
7 | 7/16"x4x9 OSB RTD | 716OSB9 | MSF | 415 | 468 | -11.32% | Wall sheathing
8 | 7/16"x4x10 OSB RTD | 716OSB10 | MSF | 415 | 468 | -11.32% | Wall/roof sheathing
9 | 1-1/8"x4x8 T&G OSB EDGGLD SIF Full Face | 118TGOSBWGOFF | MSF | 1195 | 1294 | -7.651% | Subfloor T&G
ENGINEERED LUMBER & I-JOISTS
10 | 9-1/2 BCI-5000 LF - 2" BC I-Joist | 10BCI5000 | LF | 3.19 | 3.49 | -8.596% | Floor joist
11 | 11-7/8 BCI-5000 LF - 2" BC I-Joist | 12BCI5000 | LF | 3.29 | 3.69 | -10.84% | Floor joist
12 | 5-1/2X11-7/8 Glulam LF 1.8E | 5121178DF18GL | LF | 22.29 | 25.09 | -11.16% | Glulam beam
PRESSURE TREATED LUMBER
13 | 2X6-16' #2 HF TRTD GC ICT Incised Cedartone | 2616HF2TICGC | MBF | 1363 | NEW | NEW ✦ | NEW - Deck ledger/framing
14 | 2X8-16' #2 HF TRTD GC ICT Incised Cedartone | 2816HF2TICGC | MBF | 1263 | 1232 | 2.516% | Deck framing (was PTICGC)
15 | 4X4-12' #2 HF TRTD Incised CT GC S4S | 4412HF2TICGC | MBF | 1672 | 1643 | 1.765% | Deck post
16 | 6X6-12' #2 HF TRTD Incised CT GC S4S | 6612HF2TICGC | MBF | 1883 | 2173 | -13.35% | Deck post/beam
SIDING & TRIM — FIBER CEMENT
17 | Hardi Trim Board 5/4"x3.5"x12' Rustic Grain | HZU54412RT | MSF | 6009 | 4792 | 25.4% | Hardi trim
18 | Hardi Trim Board 5/4"x5.5"x12' Rustic Grain | HZU54612RT | MSF | 6009 | 4792 | 25.4% | Hardi trim
19 | Hardi Plank Lap Siding 8.25"x12' HZ10 Cedarmill | HZ10814CMSP | MSF | 1566 | 1260 | 24.29% | Lap siding
20 | Hardi Panel 4x8 5/16" Cedarmill | HZ1048CMP | MSF | 1582 | NEW | NEW ✦ | NEW - Panel siding
CYPRESS FJ PRIMED TRIM (NEW)
21 | 5/4X4-20' Cypress FJ Primed | 540420CYPP | MBF | 4332.01 | NEW | NEW ✦ | NEW - Exterior trim
22 | 5/4X6-20' Cypress FJ Primed | 540620CYPP | MBF | 4569 | NEW | NEW ✦ | NEW - Exterior trim
23 | 2X8-20' Cypress FJ Primed | 20820CYPP | MBF | 3909 | NEW | NEW ✦ | NEW - Fascia/trim
24 | 2X6-20' Cypress FJ Primed | 20620CYPP | MBF | 3843 | NEW | NEW ✦ | NEW - Fascia/trim
25 | 1X2-20 Cypress TK FJ Primed | 10220CYPP | MBF | 3776.99 | NEW | NEW ✦ | NEW - Small trim
QUOTE TOTAL (QT# 4269124) |  |  |  | 737.15
COLOR KEY: 🔴 Pink = Price INCREASED 🟢 Green = Price DECREASED 🟡 Yellow = NEW item this quote 🔵 Blue text = Update here when prices change